## Slide 1: Project management
Lab 4

## Slide 2: Objectives
To explain the main tasks undertaken by project managers
To introduce software project management and to describe its distinctive characteristics
To discuss project planning and the planning process
To show how graphical schedule representations are used by project management

## Slide 3: Software project management
Concerned with activities involved in ensuring that software is delivered on time and on schedule and in accordance with the requirements of the organisations developing and procuring the software.
Project management is needed because software development is always subject to budget and schedule constraints that are set by the organisation developing the software.

## Slide 4: Software management distinctions
The product is intangible.
The product is uniquely flexible.
Software engineering is not recognized as an engineering discipline with the sane status as mechanical, electrical engineering, etc.
The software development process is not standardised.
Many software projects are 'one-off' projects.

## Slide 5: Management activities
Proposal writing.
Project planning and scheduling.
Project costing.
Project monitoring and reviews.
Personnel selection and evaluation.
Report writing and presentations.

## Slide 6: Project planning
Probably the most time-consuming project management activity.
Continuous activity from initial concept through to system delivery. Plans must be regularly revised as new information becomes available.
Various different types of plan may be developed to support the main software project plan that is concerned with schedule and budget.

## Slide 7: Types of project plan

## Slide 8: Project planning process
Establish the project constraints
Make initial assessments of the project parameters
Define project milestones and deliverables
while project has not been completed or cancelled loop
Draw up project schedule
Initiate activities according to schedule
Wait ( for a while )
Review project progress
Revise estimates of project parameters
Update the project schedule
Re-negotiate project constraints and deliverables
if ( problems arise ) then
Initiate technical review and possible revision
end if
end loop

## Slide 9: The project plan
The project plan sets out:
  The resources available to the project;
  The work breakdown;
  A schedule for the work.

## Slide 10: Project plan structure
Introduction.
Project organisation.
Risk analysis.
Hardware and software resource requirements.
Work breakdown.
Project schedule.
Monitoring and reporting mechanisms.

## Slide 11: Activity organization
Activities in a project should be organised to produce tangible outputs for management to judge progress.
Milestones are the end-point of a process activity.
Deliverables are project results delivered to customers.
The waterfall process allows for the straightforward definition of progress milestones.

## Slide 12: Milestones in the RE process

## Slide 13: Project scheduling
Split project into tasks and estimate time and resources required to complete each task.
Organize tasks concurrently to make optimal use of workforce.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
Dependent on project managers intuition and experience.

## Slide 14: The project scheduling process

## Slide 15: Scheduling problems
Estimating the difficulty of problems and hence the cost of developing a solution is hard.
Productivity is not proportional to the number of people working on a task.
Adding people to a late project makes it later because of communication overheads.
The unexpected always happens. Always allow contingency in planning.

## Slide 16: Bar charts and activity networks
Graphical notations used to illustrate the project schedule.
Show project breakdown into tasks. Tasks should not be too small. They should take about a week or two.
Activity charts show task dependencies and the the critical path.
Bar charts show schedule against calendar time.

## Slide 17: Task durations and dependencies

## Slide 18: Activity network

## Slide 19: Activity timeline

## Slide 20: Staff allocation

## Slide 21: Risk management
Risk management is concerned with identifying risks and drawing up plans to minimise their effect on a project.
A risk is a probability that some adverse circumstance will occur
  Project risks affect schedule or resources;
  Product risks affect the quality or performance of the software being developed;
  Business risks affect the organisation developing or procuring the software.

## Slide 22: Software risks

## Slide 23: The risk management process

## Slide 24: Risk indicators

## Slide 25: Key points
Good project management is essential for project success.
The intangible nature of software causes problems for management.
Managers have diverse roles but their most significant activities are planning, estimating and scheduling.
Planning and estimating are iterative processes which continue throughout the course of a project.

## Slide 26: Key points
A project milestone is a predictable state where a formal report of progress is presented to management.
Project scheduling involves preparing various graphical representations showing project activities, their durations and staffing.
Risk management is concerned with identifying risks which may affect the project and planning to ensure that these risks do not develop into major threats.