## Slide 1: Project planning and scheduling
Lecture 3

## Slide 2: Objectives
Introduce project planning
Examine the stages of project planning:
  Scoping
  Estimation
  Risk Analysis
  Scheduling
Focus on some of the tools and techniques available to a project planner

## Slide 3: Topics
Planning
Estimation of tasks
  Cost and time
Planning and risk
Scheduling and why projects are late
Scheduling and planning tools
Project tracking

## Slide 4: Software Project Planning
Goal is to establish a pragmatic strategy for controlling, tracking, and monitoring a complex technical project
Must deal with:
  Project complexity: has a strong effect but is heavily influenced by past practitioner experience
  Project size: as size increases the interdependency of elements also grows. Watch out for scope creep (when customers change requirements mid-cycle)
  The degree of structural uncertainty: the degree to which requirements are solidified and the ease of functional decomposition
The purpose of project planning is to ensure that the end result is completed on time, within budget, and exhibits quality!

## Slide 5: Steps in Project Planning
Scope — understand the problem and the work that must be done.
Estimation — how much effort? how much time?
Risk — what can go wrong? how can we avoid it? what can we do about it?
Schedule — how do we allocate resources along the timeline? what are the milestones?
Control strategy — how do we control quality? how do we control change?

## Slide 6: Scope
A bounded description of the data and control, function, performance, constraints, interfaces and reliability
Sufficient to determine project feasibility and create an initial plan
Scoping Techniques:
  FAST (Facilitated Application Specification Technique), QFD (Quality Function Deployment), Use-Cases
Scope is affected by:
  Customers’ needs
  Business context
  Project boundaries
  Customers’ motivation
  Likely paths for change

## Slide 7: Estimating Resources
Human Resources:
  Select skills required (both position and specialty, e.g. database software engineer). Requires an effort estimate
Reusable Software Resources:
  Off-the-shelf components (existing software acquired from 3rd party with no modification required)
  Full-experience components (previous project code is similar and team members have full experience in this application area)
  Partial-experience components (existing project code is related but requires substantial modification and team has limited experience in the application area)
  New components (must be built from scratch for this project)

## Slide 8: Estimating Resources - 2
Environmental Resources:
  The hardware and software tools required to develop the project. Planner needs to provide a time window for booking them

## Slide 9: Estimating Cost and Effort
Project scope must be explicitly defined. If not, the project may be infeasible
Task and/or functional decomposition is necessary
Historical measures (metrics) are very helpful
Triangulation: At least two different techniques should be used. Can be reconciled if they are within 20%
Remember that uncertainty is inherent in early estimates
Viable Techniques:
  Delay estimation until later in the project (XP approach)
  Base estimates on similar projects that have already been completed
  Use relatively simple decomposition techniques (LOC or FP)

## Slide 10: Risk Analysis and Management
Definition of Software Risk:
  Concerns future happenings. What risks might cause the project to go astray?
  Involves change. How will changes in customer requirements, development technologies, target computers, and other entities affect timeliness and success?
  Requires choice. What methods and tools should be used, how many people should be involved to reduce risk?

## Slide 11: Risk Analysis and Management-2
Questions:
  What can go wrong?
  What is the likelihood?
  What will the damage be?
  What can we do about it?

## Slide 12: Risk Management Paradigm

## Slide 13: Risk (3xM) Mitigation, Monitoring, and Management
Mitigation — how can we avoid the risk?
Monitoring — what factors can we track that will enable us to determine if the risk is becoming more or less likely?
Management — what contingency plans do we have if the risk occurs?

## Slide 14: Scheduling
“I love deadlines. I love the whooshing sound they make as they fly by.” – Douglas Adams
The Schedule connects the scope, work estimates and deadline into a network of SE tasks
Must Manage:
  Parallelism (tasks can be undertaken simultaneously)
  Dependency (task has an effect on subsequent tasks)
Bad Scheduling is a very destructive influence
90-90 Rule: First 90% of a project is complete in 90% of the scheduled time. The other 10% is also completed in 90% of the time

## Slide 15: Why Are Projects Late?
An unrealistic deadline established by outsiders
Changing customer requirements that are not reflected in the schedule
An honest underestimate of effort and/or resources required
Risks that were not considered when the project started

## Slide 16: Why Are Projects Late?
Technical difficulties that could not have been foreseen
Human difficulties that could not have been foreseen
Miscommunication among project staff
Project management failing to recognize schedule slippage and not taking corrective action

## Slide 17: Dealing with Unrealistic Deadlines
“Any commander in chief who undertakes to carry out a plan which he considers defective is at fault; he must put forth his reasons, insist on the plan being changed, and finally tender his resignation rather than be the instrument of his army’s downfall.” – Napoleon

## Slide 18: Tools and techniques for the planner
Scheduling
  PERT – Program Evaluation and Review Technique
  Work Breakdown Structure (WBS)
  Gantt Chart – Named after Henry Grant
ETVX – How do you track tasks

## Slide 19: Scheduling
Program Evaluation and Review Technique (PERT) AKA
  Critical Path Method (CPM) is a project scheduling method that determines:
  Critical Path (the chain of tasks that determine the duration of the project)
  Earliest Time that a task can begin if all preceding tasks are completed in the shortest possible time
  Latest Time for task initiation that will not delay the project
  Latest and Earliest Finish for the overall project
  Total Float (the maximum slippage without overall delay)
Implementation:
  Automated tools
  Often use a task network as input

## Slide 20: Define a Task Network
Task (Activity) Network: a graphical representation of the task flow and interdependencies for a project

## Slide 21: WBS – Work break down structure
What has to be done to complete the project
All the tasks in the Divide and conquer of the problem
Granularity equals level of WBS
  First level, high level tasks
  Second level are those task that complete the first level
Very similar to Outline for a paper

## Slide 22: Gantt chart
A Gantt chart provides a graphical illustration of a schedule that helps to plan, coordinate, and track specific tasks in a project
  developed in 1917 by Henry L. Gantt
A Gantt chart is constructed with a horizontal axis representing the total time span of the project, broken down into increments (for example, days, weeks, or months) and a vertical axis representing the tasks that make up the project

## Slide 23: Gantt Chart

## Slide 24: Planning individual Task expressed as ETVX
Entry Criteria
  Before starting
Tasking
Validation
Exit Criteria
  After finished

## Slide 25: How do I get the tasks? Project Planning process
“Divide and Conquer”
Divide is easy
Conquer is hard

## Slide 26: Project Planning process
Divide
  Break project up into tasks
    Estimate the “pieces”
  Bring it back together in stages (milestones)
    Tausworthe’s Principal - The more milestones the more accurate the schedule
    Corollary - The more milestones, the less time to get work done
Conquer
    Estimate completion of the divided tasks
    Gather the tasks into a whole
  Plan for testing against requirements
  Plan for delivery of product

## Slide 27: Process (Lifecycle) activation
Big bang
Waterfall
Cyclical (Spiral)
Prototyping
Rapid Application Development

## Slide 28: Resource Allocation
Use list of resources
WBS (Work Breakdown Structure)
  Tasks from estimation
  Development process being used
Gantt charts
  Parallel tasking (Resource dependent)
Pert charts
  Network of tasks

## Slide 29: Tracking the Schedule
Use list of Critical dates
When do you need the resources
When can you release the resources
Actuals vs. Estimates
  Do you have to re-plan
  Are resources over committed
Mythical Man-month
  Wall clock time vs. project time
  Trade $ for effort

## Slide 30: Effort Allocation
“front end” activities
  customer communication
  analysis
  design
  review and modification
construction activities
  coding or code generation
testing and installation
  unit, integration
  white-box, black box
  regression

## Slide 31: Tracking
The project schedule provides a roadmap for tasks and milestones that must be tracked and controlled as the project proceeds
Tracking is based on the information provided by the people completing the tasks
The ability to track a project is only as good as the data

## Slide 32: Tracking
Techniques:
Hold Periodic project status meetings for all team members
Evaluate the results of all reviews
Determine whether formal project milestones have been accomplished by the scheduled date
Comparing actual start date to planned start date for each task
Meeting informally with practitioners to obtain their subjective assessment
Using earned value analysis to assess progress quantitatively

## Slide 33: Lifecycle Planning
Lecture 4

## Slide 34: Lifecycle Defined Note: You must define terms
“Every software-development effort goes through a ‘lifecycle,’ which consists of all the activities between the time that version 1.0 of a system begins life as a gleam in someone’s eye and the time that version 6.74b finally takes its last breath on the last customers machine.”
Steve McConnell, Rapid Development, 1996

## Slide 35
“The goal is often not to achieve what you said you would do at the beginning of the project, but to achieve the
maximum possible within the time and resources available.”
Roger Sherman, Microsoft, 1995

## Slide 36: What is a Life Cycle?
Websters (1892):
  “The series of stages in form and functional activity through which an organism passes between successive recurrences of a specified primary stage.”
Reifer (1997): (product)
  “Period of time that begins when a software product is conceived and ends when the product is retired from use.”

## Slide 37: What is a Life Cycle? Tony Lattanze
The software lifecycle is the cradle to grave existence of a software product or software intensive system
  includes initial development, repairs, and enhancement, and decommission
Management of the entire lifecycle of a software intensive system requires a deeper knowledge than basic in-the-small development intuition and experience

## Slide 38
Lifecycle models attempt to generalize the software development process into steps with associated activities and/or artifacts.
  They model how a project is planned, controlled, and monitored from inception to completion.
Lifecycle models provide a starting point for defining what we will do.

## Slide 39: What is a Process?
A process is a sequence of steps performed for a given purpose.
Websters:
“a series of actions or operations conducing to an end.”
The concept of software process is rarely presented in undergraduate education.

## Slide 40: Process ≠ Lifecycle
Software process is not the same as life cycle models.
  process refers to the specific steps used in a specific organization to build systems
  indicates the specific activities that must be undertaken and artifacts that must be produced
  process definitions include more detail than provided lifecycle models

Software processes are sometimes defined in the context of a lifecycle model.

## Slide 41: Benefits of a Lifecycle Model
REPEATABLE!
Streamline project
Improve development speed
Improve quality
Improve project tracking and control
Minimize overhead
Minimize risk exposure
Improve client relations

## Slide 42: Life Cycles
Ad Hoc
Classic (waterfall)
Prototype
Throw away and evolutionary
RAD
Incremental
Spiral
Design to Schedule
Evolutionary delivery
COTS

## Slide 43: Look at with respect to:
Scope, time, resources, quality
Stakeholders
Requirements volatility
Environments
  Business / market
  Cultures
  Moral, legal constraints

## Slide 44: Ad Hoc “Hobbyist”
Legacy
Code – Test – Code – Test………
  Becomes a mess, chuck it, start over

Design (high level) – Code – Test – Code – Test…..
  (Reality was Code - Test – Code – Test – Document the resulting design)

Maintenance Phase: Test – Code - Test

## Slide 45: Waterfall Model also called traditional
First proposed in 1970 by W.W. Royce

Development flows steadily through:
  requirements analysis, design implementation, testing, integration, and maintenance.
Note: Royce advocated iterations of waterfalls adapting the results of the precedent waterfall.

## Slide 46: Waterfall Model
Technology had some influence on the viability of the waterfall model.
 slow code, compile, and debug cycles
Reflected the way that other engineering disciplines build things.
Formed the basis of the earliest software process frameworks
Waterfall is still used today (but no one will admit it)

## Slide 47: Waterfall Model Intent
Benefits:
  Logical Sequence
  Highly Scalable
  Artifact/document driven
  Set milestones / review points

## Slide 48: Waterfall Model: Reality

## Slide 49: Waterfall Problems
Need for “big specification” (requirements)
Inflexible
Increasing use of resources?
  Oops
    Go back to a previous step
    Progressively more costly
No results till end
Possible cost of cascading bugs
Importance of secondary artifacts
Where appropriate?

## Slide 50: Throw away Prototype
Proof of concept – It can be done
End point unknown!
Goal is domain knowledge increase
Disadvantages
  Seen as project completion
    But not robust
  Quality

## Slide 51: Evolutionary Prototype
Keep something
Different than incremental?
The evolutionary development model can be distinguished from the prototyping model in that
  a final product is typically specified  the product features are evolved overtime to some predetermined final state
Develop system concept as the project progresses
Begin with the most visible aspects
Prototype

## Slide 52: The Rapid Prototype Model

## Slide 53: A Common Misuse of the Rapid Prototype Model

## Slide 54: Incremental Typical Agile Model
The incremental model prescribes developing and delivering the product in planned increments.
  The product is designed to be delivered in increments.
  Each increment provides (in theory) more functionality than the previous increment.
How is this different from Evolutionary?

## Slide 55: Incremental / Agile methods
Customer centric – customer expectation management
  Deliver every increment
  Develop the product with tight customer involvement
  Use customer needs to drive priorities for the project
Similar in many aspects to “rapid prototyping”
Use “small team” integration to handle many project issues
  Scrum and XP are primary examples

## Slide 56: Agile Advantages & Disadvantages
Advantages
  Highly Flexible – volatile requirements
  Works on what is important for the customer
  Primary artifact is Code
  Short increments reduce failure impact
  Use teaming controls to improve quality
Disadvantages
  Team co-location required - maybe
  Scope is looked at in “short cycles”
    “What can be done in a week”
  Drive towards product only focus
    Maintenance issues
    Documentation – Legal, safety of life
    Design on the fly
  Scalability

## Slide 57: Rapid Application Development (RAD)
Incremental
60-90 days per release
Information Systems
4th Generation Techniques

## Slide 58: Spiral Model
The spiral model
  First defined by Barry Boehm
  combines elements of:
    evolutionary, incremental, and prototyping models
  First model to explain
    why iteration matters
    How iteration could be used effectively
  the term spiral refers successive iterations outward from a central starting point.

## Slide 59: Spiral Model

## Slide 60: Spiral Model
The goal is to identify risk and focus on it early.
In theory, risk is reduced in outer spirals as the product becomes more refined.
  Cost/time increases reduce risk
Each spiral
  starts with design goals
  ends with the client reviewing the progress thus far and future direction
  was originally prescribed to last up to 2 years
Flexible

## Slide 61: Possible Applications
High risk projects
  Poorly understood requirements
  Poorly understood architecture
  Potential performance problems
  Problems in the underlying technology
Combine with other lifecycle models
  Terminate with waterfall or other lifecycle
  Incorporate other lifecycle models as iterations

## Slide 62: Design-to-Schedule
Prioritize features
Unsure if final release will be reached

## Slide 63: Design-to-Schedule Benefits
Ensure product release for a particular date
Most important features completed first
Useful for project parts not on the critical path

## Slide 64: Design-to-Schedule Disadvantages
Wasted effort specifying unfinished stages
  Could complete one or more stages if time was not wasted specifying several unfinished stages

## Slide 65: Evolutionary Delivery
Similar to Evolutionary Prototyping
Refine version based upon customer feedback
Emphasizes core of the system

## Slide 66: Evolutionary Delivery
Benefits
  Can accommodate customer requests
  Allows a degree of midcourse changes
  Provides tangible results
Disadvantages
  Requires careful planning
  May lead to Code-and-Fix development
Use for Exceptionally time-sensitive projects

## Slide 67: Commercial Off-the-Shelf Software
Cycle
  Identify Possible ones
  Check Library
  Use (if they exist)
  Build new ones (if they don’t
  Put new ones in Library
But: Software rarely matches ideal software
  Design concessions
  Cost concessions
  Schedule concessions

## Slide 68: Choosing: Criteria to consider
Requirements understood? Volatile?
Scope of project
External constraints?
Need for design / architecture
Quality
Future revisions?
How much risk can you accept
Schedule / Resource constraints

## Slide 69: Choosing An Appropriate Lifecycle
Need to provide visible progress to customers
Need to provide visible progress to management
How sophisticated (complicated) is the model

## Slide 70: Strengths & Weaknesses

## Slide 71: Strengths & Weaknesses

## Slide 72: Strengths & Weaknesses

## Slide 73: Common Errors in Choosing
Tailoring project to fit lifecycle
  Looking for a recipe
  NO! Tailor lifecycle
  Imbedded lifecycles
Supermarket approach
  Pick and choose?
It must be repeatable!